## Instructions
This Workbook is a companion to the Virtual Exercise Best Practices Guide.
This workbook has two tabs (see below). Both will help you plan and conduct your virtual exercise.
These considerations are platform agnostic - use them to evaluate your options.
Early testing and research is critical to optimizing your virtual platform to reach your exercise objectives.
Each tab has specific instructions on how to use and tailor the considerations for your specific exercise and stakeholder needs.
Tab Name | Tab Use
Platform Comparison | Use this tab to ASSESS PLATFORM FEATURES to help you SELECT THE BEST FIT
Virtual Master Task List | Use this tab to TRACK THE STATUS OF TASKS as you prep and conduct your exercise

## Sample Platform Comparison
This Workbook is a companion to the Virtual Exercise Best Practices Guide.
Use this tab to ASSESS PLATFORM FEATURES to help you SELECT THE BEST FIT
1. Columns A, B, and C are common platform feature considerations.
2. Use columns D, E, and F to take notes on the platforms you are considering (see examples).
3. Add rows for additional considerations that are important to your exercise.
4. Use the dropdown feature on the column headings to sort or filter for your key considerations.
Phase | Feature | Consider this: | What Are My Requirements and Limitations? | Does This Platform Meet My Requirements? | Notes
Pre-conduct | Suitability of Existing Organization Platform | Whether external users can be authorized to access it | My organization must be the host. I require external partners to be able to join and participate via audio and chat. Webcam functionality is not critical. | Yes | This platform only allows external connections if the meeting settings are changed before opening the meeting.
Pre-conduct | Suitability of Existing Organization Platform | Software, version compatibility or hardware requirements to use it effectively | Only version XXX of the application functions on my organizations computer. | Yes | Confirm version # with IT support
Pre-conduct | Suitability of Existing Organization Platform | Any use or feature restrictions | File hosting | Yes - with exceptions | Certain partners have the file hosting and accessibility option disabled and must be sent all files through other means
Pre-conduct | Suitability of Existing Organization Platform | Potential bandwidth issues or impacts of other platforms that may be in use during the exercise | My organization requires access to official email during the exercise. | Yes | Advise all partners to limit other programs and ensure they connect via ethernet or strong Wi-Fi. Limit use of webcams.
Pre-conduct | Suitability of Existing Organization Platform | Any impacts the Virtual Private Network (VPN) or other applications may have (e.g., limiting bandwidth, blocking platforms). | VPN use is required for host and for my organization to run other critical work programs in parallel. VPN not required for external participants. | Yes | Advise external partners to avoid VPN use if able
Pre-conduct | Suitability of Existing Organization Platform | Whether the set of meetings can use different platforms for those with external attendees (versus ones just within your organization)
Pre-conduct | Application and Web Browser Differences | Whether the browser or application version has any reduced or loss of functionality | Hosts must use the application version. All other participants can use the browser. | Yes | Browser version retain same functionality but has a different interface. Update user guide.
Pre-conduct | Application and Web Browser Differences | Whether the platform requires external users to use a particular version (application or browser) | No requirements. Some organizations may have limitations due to their IT policies | Yes | XXX Partner is limited to browser version only.
Pre-conduct | CUI Compliance | Whether the selected platform can host discussions at the appropriate security level and has appropriate cybersecurity protections. (FOUO/CUI compliant and encryption) | Data encryption and FOUO compliance. | Yes | Consulted with IT and security offices. Ensure all material is marked and a security briefing is provided upfront and at the end of the exercise. Platform has data encryption.
Pre-conduct | CUI Compliance | Whether the platform has built-in access controls | Host requires a waiting room or holding feature to validate the user attempting to join. The discussion and material is not meant for the public or users without the need to know. | No | Hosts must open up the meeting room one hour early, allow users in, and validate each individual in plenary setting unless their name/org matches the RSVP roster.
Pre-conduct | CUI Compliance | Whether the platform's recording capabilities have use authorization | My organization requires the recording of this exercise for the benefit of other partners, record keeping, and future audits | No | This platform does not have built-in recording. Pursue alternative options or an exemption to policy.
Conduct | Chat Function | Whether participants can use chat to sign in and communicate with each other during the exercise | Host requires all participants to have access to group chat. | Yes | No restrictions across any version or partner.
Conduct | Chat Function | Whether the platform's interactive features support the objectives. (e.g. (Chat, Raise Hand, Polling, Share Screen, Reactions) | Host requires use of chat, hand raise, and screen share | Yes | No restrictions on these features. They function across all partners and versions. Screen sharing must be limited to the host
Conduct | Chat Function | If the platform can capture the chat box for further review and feedback at a later time | Host requires copying the chat into another document | No | Chat box can be incorporated for feedback but must be manually saved by a planning team member
Pre-conduct | Access and Functional Needs | Whether the platform had built-in disability and access and functional needs features and if 3rd party support is required.(FedRelay) | Closed Captioning | No | Pursue 3rd party support for closed captioning and review RSVP information for other requirements.
Pre-conduct | Recording Capabilities | The positive and negative consequences of recording the exercise | My organization requires the recording of this exercise for the benefit of other partners, record keeping, and future audits | No | Participants may chose to no participate or limit their participation if recorded.
Pre-conduct | Recording Capabilities | Whether the platform's breakout rooms have recording capabilities | My organization requires the recording of this exercise for the benefit of other partners, record keeping, and future audits | No | See row 19
Conduct | Teleconference Integration and Audio | Whether the platform's audio capability/quality is sufficient, does it allow dial-in users, or is an external teleconference required | Built-in audio channel with teleconference integration for plenary and breakouts | Yes | Advise users to use the platform and PC based audio first, phone dial-in only if needed. 3rd party teleconference not required.
Conduct | Teleconference Integration and Audio | The different ways the platform offers users to connect to the audio channel (computer, phone or tablet tied to their platform log-in) | No limitations. Desire to offer as many connection opportunities as possible. | Yes | This platform works best when a users audio is tied to their log-in. Direct dial-in users for audio only display as XXX-XXXX and must be identified by the host.
Conduct | Teleconference Integration and Audio | Whether there is a smart phone or work tablet app for users | Limitations on what features can be used on a phone | Yes | The smart phone capability must have a user unmute themselves on their phone and headset in order to speak
Conduct | Teleconference Integration and Audio | Whether the platform provides a direct dial-in via a phone number and passcode that identifies the participant without a platform log-in | No limitations. Desire to offer as many connection opportunities as possible. | Yes | Host must ensure the passcode is protected and all phone only users are identified before STARTEX
Conduct | Teleconference Integration and Audio | Whether the platform allows the host(s) a "mute all" function | Host requires the ability to mute all audio input | Yes | Host has access to increased privileges
Conduct | Multiple Hosts | Whether the platform offers the administrator controls needed for the exercise | Access control, mute/webcam toggle, screen share, screen name editing | Yes | No issues. Must train host how to edit user screen names to meet the standard of title, name, org.
Conduct | Multiple Hosts | Whether the platform allows external users to be hosts | No requirements. All hosts will be internal | Yes | No issues
Conduct | Multiple Hosts | Whether the platform allows multiple hosts (giving you task sharing capability and backup options) | Require two simultaneous hosts for continuity | Yes | Primary host must assign privileges to secondary host before STARTEX
Conduct | Breakout Sessions | Whether this platform has breakout functionality or if a separate unique meeting room is required to mimic breakout functionality | Require two simultaneous breakout rooms that can be assigned to individual participants and the ability to pull them back into plenary | Yes | Host and staff must train on how to manage breakout groups. Participants must be informed of what to expect from a user's perspective.
Conduct | Breakout Sessions | Whether breakouts have their own audio channel and chat | Require each breakout to have its own unique audio channel with all the capabilities of the plenary and a unique chat function | Yes | Phone only users must disconnect and reconnect with specific passcode to their breakout session. The program cannot migrate phone only users from plenary into breakout.
Conduct | Breakout Sessions | Whether breakouts allow phone-only users | Required | Yes | See row 33
Conduct | Chat in Multiple Languages | Whether the platform has built-in language translation | Not required | Yes | No issues

## Platform Comparison
This Workbook is a companion to the Virtual Exercise Best Practices Guide.
Use this tab to ASSESS PLATFORM FEATURES to help you SELECT THE BEST FIT
1. Columns A, B, and C are common platform feature considerations.
2. Use columns D, E, and F to take notes on the platforms you are considering (see examples).
3. Add rows for additional considerations that are important to your exercise.
4. Use the dropdown feature on the column headings to sort or filter for your key considerations.
Phase | Feature | Consider this: | What Are My Requirements and Limitations? | Does This Platform Meet My Requirements? | Notes
Pre-conduct | Suitability of Existing Organization Platform | Whether external users can be authorized to access it
Pre-conduct | Suitability of Existing Organization Platform | Software, version compatibility or hardware requirements to use it effectively
Pre-conduct | Suitability of Existing Organization Platform | Any use or feature restrictions
Pre-conduct | Suitability of Existing Organization Platform | Potential bandwidth issues or impacts of other platforms that may be in use during the exercise
Pre-conduct | Suitability of Existing Organization Platform | Any impacts the Virtual Private Network (VPN) or other applications may have (e.g., limiting bandwidth, blocking platforms).
Pre-conduct | Suitability of Existing Organization Platform | Whether the set of meetings can use different platforms for those with external attendees (versus ones just within your organization)
Pre-conduct | Application and Web Browser Differences | Whether the browser or application version has any reduced or loss of functionality
Pre-conduct | Application and Web Browser Differences | Whether the platform requires external users to use a particular version (application or browser)
Pre-conduct | CUI Compliance | Whether the selected platform can host discussions at the appropriate security level and has appropriate cybersecurity protections. (FOUO/CUI compliant and encryption)
Pre-conduct | CUI Compliance | Whether the platform has built-in access controls
Pre-conduct | CUI Compliance | Whether the platform's recording capabilities have use authorization
Conduct | Chat Function | Whether participants can use chat to sign in and communicate with each other during the exercise
Conduct | Chat Function | Whether the platform's interactive features support the objectives. (e.g. (Chat, Raise Hand, Polling, Share Screen, Reactions)
Conduct | Chat Function | If the platform can capture the chat box for further review and feedback at a later time
Pre-conduct | Access and Functional Needs | Whether the platform had built-in access and functional needs features and if 3rd party support is required.(FedRelay)
Pre-conduct | Recording Capabilities | The positive and negative consequences of recording the exercise
Pre-conduct | Recording Capabilities | Whether the platform's breakout rooms have recording capabilities
Conduct | Teleconference Integration and Audio | Whether the platform's audio capability/quality is sufficient, does it allow dial-in users, or is an external teleconference required
Conduct | Teleconference Integration and Audio | The different ways the platform offers users to connect to the audio channel (computer, phone or tablet tied to their platform log-in)
Conduct | Teleconference Integration and Audio | Whether there is a smart phone or work tablet app for users
Conduct | Teleconference Integration and Audio | Whether the platform provides a direct dial-in via a phone number and passcode that identifies the participant without a platform log-in
Conduct | Teleconference Integration and Audio | Whether the platform allows the host(s) a "mute all" function
Conduct | Multiple Hosts | Whether the platform offers the administrator controls needed for the exercise
Conduct | Multiple Hosts | Whether the platform allows external users to be hosts
Conduct | Multiple Hosts | Whether the platform allows multiple hosts (giving you task sharing capability and backup options)
Conduct | Breakout Sessions | Whether this platform has breakout functionality or if a separate unique meeting room is required to mimic breakout functionality
Conduct | Breakout Sessions | Whether breakouts have their own audio channel and chat
Conduct | Breakout Sessions | Whether breakouts allow phone-only users
Conduct | Chat in Multiple Languages | Whether the platform has built-in language translation

## Sample Virtual Task List
This Workbook is a companion to the Virtual Exercise Best Practices Guide.
Use this tab to TRACK THE STATUS OF TASKS as you prep and conduct your exercise
1. Columns A, B, and C are tasks and subtasks with common considerations.
2. Use column D to track tasks to completion.
3. Use column E for notes (see examples).
4. Add rows for additional tasks that are important to your exercise.
5. Use the dropdown feature on the column headings to sort or filter to check status of key items.
Task | Subtask | Considerations | Status | Notes
Platform Testing Sessions | Confirm an acceptable platform has been chosen | Verify use with exercise planning team | Complete
Platform Testing Sessions | Test with exercise planning team | All roles assigned and validated | Incomplete
Platform Testing Sessions | Multiple tests with registered and approved participants | Review procedure, etiquette, and interactive feature use expectations | Incomplete
Invitations to Participants | Confirm a registration/vetting process is in place | Use an online registration tool or excel spreadsheet to keep track of participants | Complete
Invitations to Participants | Confirm decisions on how to send invitations have been made | Determine how many players and observers from each agency will be attending, so that the invitations can be sent to them | Complete
Invitations to Participants | Provide information on connecting to virtual platform and contingency platform and user guide as needed. | Include how early before STARTEX users are expected to sign on. | Complete
Invitations to Participants | Include Read-Ahead Documentation | Read-ahead documentation can include the scenario, key issues and discussion questions and the virtual platform user guide. | Complete
Invitations to Participants | Consider multiple time zones as needed | An agenda for different time zones should accommodate those who need longer lunch breaks or later start times | Complete
Invitations to Participants | Determine exercise classification and restriction level to regulate number of invites and limit of invite forwards | Ensure participants understand applicable OPSEC considerations. | Complete
Invitations to Participants | All participants pre-exercise responses and inquiries concerning exercise conduct | Follow up with participants where needed and confirm platform login, audio and display have been addressed | Complete
Track Participation | Highlight/list critical participants and key speakers | Require these users attend testing session(s) and a facilitator is tracking them | Incomplete
Track Participation | Ensure panelists, briefers and guests are prepared for role | Elevate permissions if required; procure their conduct slides as needed | Complete
Track Participation | Provide operational security requirements to planning team and participants as needed | Participants should be able to input their agency or organization in time for the start of the exercise | Complete
Track Participation | Track participants as they enter and leave the meeting space | Synchronize with chosen access control measures | Complete
Track Participation | Track names and agency/organization of all participants to create a record | Assign roles early, including which agency representative is a key speaker, player or observer | Complete
Prepare Exercise Staff | Confirm you have a complete list of exercise staff asssiting with the conduct of the exercise | Make sure you have the backups to primary roles on your list | Incomplete
Prepare Exercise Staff | Assign required exercise roles to exercise staff and fill any role unassigned | Minimum: host/facilitator/troubleshooter and interactive feature monitors | Complete
Prepare Exercise Staff | Provide staff with training on administrator controls and elevated permissions | Schedule technology tests for staff in advance of the exercise, in order for them to become familiar with the features and permissions | Complete
Prepare Exercise Staff | Conduct multiple rehearsals to run through the exercise conduct slides and test the audio and visual requirements | Conduct at least 2 rehearsals starting no later than 1 week prior to exercise conduct | Complete
Prepare Exercise Staff | Develop and provide technology contingency plan and backup roles document | Develop a table of roles and responsibilities for each members, as well as contact information for troubleshooters during conduct | Complete
Prepare Exercise Staff | Determine whether staff should record the event | Consider compliance with applicable regulations or leadership decisions. | Complete
Prepare Platform/Meeting Space | Exercise staff enter the platform room early | Confirm staff roles, share the slides, conduct a roll call for early participants | Complete
Prepare Platform/Meeting Space | Test and practice all features being used | Confirm breakout functionality | Incomplete
Prepare Platform/Meeting Space | Set up all features prior to the start of the exercise | Consider the format of the meeting space, access controls, breakout rooms, uploading files, sharing conduct slides, providing reasonable accommodations | Complete
Prepare Platform/Meeting Space | Open meeting room at least 1 hour before STARTEX | Pre-STARTEX time scales with the size of your exercise. | Complete
Prepare Platform/Meeting Space | Provide room opening time in read ahead material and official invitation | Room open time is different than STARTEX - confirm importance of arriving BEFORE STARTEX | Complete
Exercise Closeout | Leave the room open for an additiona 15-30 minutes to provide participants with time to fill in feedback forms or discuss key topics during the exercise | 2 exercise planning team members should stay for the duration of this time | Incomplete
Exercise Closeout | In case the exercise runs over, add additional time to the meeting invite | Provide at least 30 minutes of additional time, in case exercise play runs over the allotted agenda time | Complete
Exercise Closeout | Ensure a hotwash has been conducted with participants | Provide time within the agenda to gather information on gaps and improvements of the plan from participants | Complete
Exercise Closeout | Conduct a debrief with exercise planning team members after the exercise | Create an additional virtual meeting to allow planning team members to provide feedback on exercise design and evaluation notes | Complete

## Virtual Master Task List
This Workbook is a companion to the Virtual Exercise Best Practices Guide.
Use this tab to TRACK THE STATUS OF TASKS as you prep and conduct your exercise
1. Columns A, B, and C are tasks and subtasks with common considerations.
2. Use column D to track tasks to completion.
3. Use column E for notes (see examples).
4. Add rows for additional tasks that are important to your exercise.
5. Use the dropdown feature on the column headings to sort or filter to check status of key items.
Task | Subtask | Considerations | Status | Notes
Platform Testing Sessions | Confirm an acceptable platform has been chosen | Verify use with exercise planning team
Platform Testing Sessions | Test with exercise planning team | All roles assigned and validated
Platform Testing Sessions | Multiple tests with registered and approved participants | Review procedure, etiquette, and interactive feature use expectations
Invitations to Participants | Confirm a registration/vetting process is in place | Use an online registration tool or excel spreadsheet to keep track of participants
Invitations to Participants | Confirm decisions on how to send invitations have been made | Determine how many players and observers from each agency will be attending, so that the invitations can be sent to them
Invitations to Participants | Provide information on connecting to virtual platform and contingency platform and user guide as needed. | Include how early before STARTEX users are expected to sign on.
Invitations to Participants | Include Read-Ahead Documentation | Read-ahead documentation can include the scenario, key issues and discussion questions and the virtual platform user guide.
Invitations to Participants | Consider multiple time zones as needed | An agenda for different time zones should accommodate those who need longer lunch breaks or later start times
Invitations to Participants | Determine exercise classification and restriction level to regulate number of invites and limit of invite forwards | Ensure participants understand applicable OPSEC considerations.
Invitations to Participants | All participants pre-exercise responses and inquiries concerning exercise conduct | Follow up with participants where needed and confirm platform login, audio and display have been addressed
Track Participation | Highlight/list critical participants and key speakers | Require these users attend testing session(s) and a facilitator is tracking them
Track Participation | Ensure panelists, briefers and guests are prepared for role | Elevate permissions if required; procure their conduct slides as needed
Track Participation | Provide operational security requirements to planning team and participants as needed | Participants should be able to input their agency or organization in time for the start of the exercise
Track Participation | Track participants as they enter and leave the meeting space | Synchronize with chosen access control measures
Track Participation | Track names and agency/organization of all participants to create a record | Assign roles early, including which agency representative is a key speaker, player or observer
Prepare Exercise Staff | Confirm you have a complete list of exercise staff asssiting with the conduct of the exercise | Make sure you have the backups to primary roles on your list
Prepare Exercise Staff | Assign required exercise roles to exercise staff and fill any role unassigned | Minimum: host/facilitator/troubleshooter and interactive feature monitors
Prepare Exercise Staff | Provide staff with training on administrator controls and elevated permissions | Schedule technology tests for staff in advance of the exercise, in order for them to become familiar with the features and permissions
Prepare Exercise Staff | Conduct multiple rehearsals to run through the exercise conduct slides and test the audio and visual requirements | Conduct at least 2 rehearsals starting no later than 1 week prior to exercise conduct
Prepare Exercise Staff | Develop and provide technology contingency plan and backup roles document | Develop a table of roles and responsibilities for each members, as well as contact information for troubleshooters during conduct
Prepare Exercise Staff | Determine whether staff should record the event | Consider compliance with applicable regulations or leadership decisions.
Prepare Platform/Meeting Space | Exercise staff enter the platform room early | Confirm staff roles, share the slides, conduct a roll call for early participants
Prepare Platform/Meeting Space | Test and practice all features being used | Confirm breakout functionality
Prepare Platform/Meeting Space | Set up all features prior to the start of the exercise | Consider the format of the meeting space, access controls, breakout rooms, uploading files, sharing conduct slides, providing reasonable accommodations
Prepare Platform/Meeting Space | Open meeting room at least 1 hour before STARTEX | Pre-STARTEX time scales with the size of your exercise.
Prepare Platform/Meeting Space | Provide room opening time in read ahead material and official invitation | Room open time is different than STARTEX - confirm importance of arriving BEFORE STARTEX
Exercise Closeout | Leave the room open for an additiona 15-30 minutes to provide participants with time to fill in feedback forms or discuss key topics during the exercise | 2 exercise planning team members should stay for the duration of this time
Exercise Closeout | In case the exercise runs over, add additional time to the meeting invite | Provide at least 30 minutes of additional time, in case exercise play runs over the allotted agenda time
Exercise Closeout | Ensure a hotwash has been conducted with participants | Provide time within the agenda to gather information on gaps and improvements of the plan from participants
Exercise Closeout | Conduct a debrief with exercise planning team members after the exercise | Create an additional virtual meeting to allow planning team members to provide feedback on exercise design and evaluation notes